## Values (hidden)
likelihood | decision | status
Very low | Acceptance | Open
Low | Mitigation | In progress
Medium | Transfer | Closed
High | Avoidance
Critical

## Assessment
Risk Id | R0001
Asset | Coffee |  | Owner | Scrooge McDuck
Scenario | Main supplier fails to deliver
Consequences | People go crazy
CIA
|  |  | Comment | Cost is not an issue here
Impact | Very low
Likelihood | Very low |  | Decision | Mitigation
Risk | VERY LOW |  | Status | In progress
R01
Current compensating controls |  |  | Mitigation action list
# | Description |  | # | Who | When | Description
1 | We have a 3 day rolling stock |  | 1 | Huey | 2022-07-01 | Get coffee from StarBucks
2 |  |  | 2 | Dewey | 2022-07-01 | Get coffee from Dunkin Donuts
3 |  |  | 3 | Louie | 2022-07-01 | Get coffee from McDonalds
4 |  |  | 4
5 |  |  | 5
6 |  |  | 6
7 |  |  | 7
8 |  |  | 8
Risk Id | R0002
Asset | Coffee |  | Owner | Scrooge McDuck
Scenario | There's mold on the beans
Consequences | People get sick
CIA
Comment
Impact | Critical
Likelihood | Very low |  | Decision
Risk | MEDIUM |  | Status | Open
R11
Current compensating controls |  |  | action list
# | Description |  | # | Who | When | Description
1 |  |  | 1
2 |  |  | 2
3 |  |  | 3
4 |  |  | 4
5 |  |  | 5
6 |  |  | 6
7 |  |  | 7
8 |  |  | 8
Risk Id | R0003
Asset | Coffee |  | Owner | Scrooge McDuck
Scenario | Our secret blend is leaked
Consequences | Competition uses it and become as productive as us
CIA
|  |  | Comment | This is our most precious information!
Impact | Critical
Likelihood | Medium |  | Decision | Mitigation
Risk | CRITICAL |  | Status | Closed
Current compensating controls |  | C20 | Mitigation action list
# | Description |  | # | Who | When | Description
1 |  |  | 1 | Huey | 2022-06-22 | Buy a safe
2 |  |  | 2 | Scrooge McDuck | 2022-06-22 | Put recipe in a safe
3 |  |  | 3
4 |  |  | 4
5 |  |  | 5
6 |  |  | 6
7 |  |  | 7
8 |  |  | 8
Confidentiality
Integrity
Availability
Confidentiality
Integrity
Availability
Confidentiality
Integrity
Availability

## Register
Risk # | Asset | Risk (Scenario ==> Consequence) | Owner | Risk | Decision | Status | Action plan | Comment
R0001 | Coffee | People go crazy ==> Main supplier fails to deliver | Scrooge McDuck | VERY LOW | Mitigation | In progress | Huey (7/22) Get coffee from StarBucks Dewey (7/22) Get coffee from Dunkin Donuts Louie (7/22) Get coffee from McDonalds | Cost is not an issue here
R0002 | Coffee | People get sick ==> There's mold on the beans | Scrooge McDuck | MEDIUM |  | Open
R0003 | Coffee | Competition uses it and become as productive as us ==> Our secret blend is leaked | Scrooge McDuck | CRITICAL | Mitigation | Closed | Huey (6/22) Buy a safe Scrooge McDuck (6/22) Put recipe in a safe | This is our most precious information!

## Map
| OPEN RISKS | [6 empty] | CLOSED RISKS
Likelihood | Critical | [5 empty] | Likelihood | Critical
| High | [6 empty] | High
| Medium | [6 empty] | Medium |  |  |  |  | 1
| Low | [6 empty] | Low
| Very low | 1 |  |  |  | 1 |  | Very low
|  | Very low | Low | Medium | High | Critical |  |  | Very low | Low | Medium | High | Critical
|  | Impact | [6 empty] | Impact